## MIRA (hidden)
Sr. No. | Date | Name | Opportunities/Initiatives | Effort Estimate (in hours) | Estimated Savings (Per year in hours) | Priority | Implementation Status | Assigned To | Comments
1 | 2017-03-01 | Sourav | Avoid JVM Heap Size Error | 20 | 39 |  | Planned | Sourav | Currently we are receivie alert message for Max Heap size error. It can be stopped by archiving the log.
2 | 2017-03-01 | Sourav | Alert when application is down | 20 | 40 |  | Inprogress | Sourav | It will intimate support Team through mail whenever MSTR application goes down inside the server. It will save around 1 hr per outage.
3 | 2017-03-01 | Sourav | Create logs for high CPU utilization | 10 | 0 |  | Planned | Sourav | This script will logs the max CPU consuming process with process details on a hourly basis. It will help the team to analyze outages. It will help for proactive monitoring.
4 | 2017-03-01 | Sourav | Modify the alert for high CPU utilization | 10 | 30 |  | Planned | Sourav | If CPU utilization alarm is reduced from 1hr to 30 minutes, it will save 30 mins in each outage.
5 | 2017-03-01 | Rishi | Automation of user creation in MSTR in ASPAC | 10 | 96 | Q1 | Completed | Rishiraj | - Average of 15 user requests per month i.e. 180 per year - Today - Addition of one user 10 mins - After implementation - 2 mins
6 | 2017-03-01 | Rishi | Automation of user creation in MSTR in EMEA | 10 | 96 | Q1 | Completed | Rishiraj
7 | 2017-03-01 | Rishi | Automation of user creation in MSTR in NA | 10 | 96 | Q1 | Completed | Rishiraj
8 | 2017-03-01 | Rishi | Automation SLT email notification | 25 | 20.8333 |  | Planned | Rishiraj | Today - Wait for load and send the email 5 mins After implementation - 0 mins Assuming
9 | 2017-03-01 | Ramya | Option to delete user specific cache on Ipad | 40 | 12 |  | Planned |  | 4 tickets per month. 1 ticket takes 15mins
10 | 2017-03-01 | Ramya | Trigger jobs only when files are available (ASPAC, LFSCGPS) | 60 | 720 |  | Planned |  | each region requires 1hr/day to monitor
11 | 2017-03-01 | Raghavendra | Automate daily reconciliation of NA Vistakon Sales data | 60 | 384 |  | 4/12- On-hold Analysis in progress | Shankar | Reduction in data mismatch incidents; approx 2 per month; savings: 16 hrs per incident
12 | 2017-03-01 | Raghavendra | Automating the migration tasks (DB) | 16 | 18 |  | Planned | Shekar | Savings: 25 mins per deployment; Assumption: 2 deployments per month (QA/PROD); 3 regions
13 | 2017-03-01 | Raghavendra | ETL package to add multiple users NA | 8 | 96 |  | Planned | Kavya | Savings: 1 hr/request; approx 8 tickets per month
14 | 2017-03-01 | Raghavendra | Optimize LifeScan GPS ETL to run multiple downloads from MBOX in parallel | 8 | 6 |  | Planned | Muthu | This is performance optimization. Savings: 25 mins per job run when executed manually when failed; approx 2 failures in a month
15 | 2017-03-01 | Raghavendra | Dcoumentation of steps for resolution of incident |  |  |  | Planned |  | This falls under process improvement.
16 | 2017-03-01 | Vijay | MSTR Subscription based on ETL load completion. | 40 | 125 |  | MSTR part is completed. On -hold due to NA sync. |  | 20 hrs - MSTR 20 hrs - ETL Assuming 250 working days in a year and half hour of wait time is the load doesnt happen in time.
17 | 2017-03-01 | Vijay | Automation MSTR cache deletion - ASPAC and Japan | 40 | 41.66 | Q1 | Completed | Rishiraj | time for monitoring + manual deletion of cache (yearly) estimation only numbers put in comments the explanation 5 mins wait time + 5 mins cache clearing
18 | 2017-03-01 | Vijay | Automation MSTR cache deletion - LifeScan EMEA | 24 | 41.66 | Q1 | Completed | Rishiraj | Same as above
19 | 2017-03-01 | Vijay | Automation MSTR cache deletion - NA | 24 | 41.66 |  | On-Hold | Rishiraj | Same as above
20 | 2017-04-01 | Shankar | Automate the daily job monitory activity (dashboard to view all jobs) | 200 | 237.6 |  |  |  | Savings: 15 mins per server; 6 servers; 5 days per week
21 | 2017-04-01 | Ramya | Automation of Year End Activities (ASPAC & NA) | 60 | 80 |  |  |  | 5 incidents last year since periodic tables were not updated
22 | 2017-04-01 | Ramya | Implement delete and archive for NA ETL instead of copy and paste | 50 | 40 |  |  |  | recieved one incident because of which data was duplicated. implement better etl solutions like archiving files and deleting the files.
23 | 2017-04-01 | Ramya | Automate the Japan KPI Metrics from Enterprise Manager | 60 | 192 |  |  |  | Savings:16hrs/month. This activity has to be done every month
24 | 2017-04-01 | Ramya | automation of cube refresh for my acuvue | 2 | 90 | Q1 | Completed |  | Savings: 15mins/day
25 | 2017-04-01 | Shekar | MBOX configuration for NA Call Files | 4 | 104 |  | Inprogress | Shekar | Savings: 2hrs per week
26 | 2017-04-01 | Rishi | Template for regression suite | 2 | 3 | Q1 | Completed | Rishiraj | On an average, there are 3 major version updates for every iOS version; 3 times creation of testing suite will take 1 hour each
27 | 2017-04-01 | Raghavendra | Automate Vistakon NA SSIS project version switch over | 2 | 132 |  | Inprogress | Shekar | Savings: 30mins/day, 5 days per week
28 | 2017-04-01 | Shekar | ASPAC Japan Sunday job schedule | 3 | 208 | Q1 |  | Shekar | Job runs on Sun & Mon; Savings: 4 hrs per week
29 | 2017-04-01 | Shankar | Environment Sync -> creation of ETL to load data from PROD to QA | 16 | 24 |  |  |  | Savings: 2 hr for each sync; approx 1 env sync requests per month due to data mismatch between prod & qa
30 | 2017-04-17 | Rishi | Syncronization of qa and prod environments
31 | 2017-04-17 | Shankar | Automate data load in --> FACT_EXPECTED_GROWTH | 24 | 20 | Q2 |  |  | Savings:5 hrs/Per Quarter. This activity has to be done every Quarter
Automation of MSTR cache refresh. It reduces lots of manual work and also reduces 30 incidents in an year
Automation of cube refresh of myAcuvue. It reduces 90 hours of manual work per year.
Automate Vistakon NA SSIS project version switch over. It reduces 130 hour of manual work per year.
Segregation of tickets based on region and environment. There was no separate configuration item in IRIS for dev and qa so all ticket by default was assigned to production configuration item in IRIS. It helps identifiying environment

## CMT (hidden)
Service Improvement | Priority | No. of SR's/ Month | Estimates | Benefits | Status | Comments
a. Oracle Auto stat is enabled, need to see if we can move auto stat window. Ihor to initiate discussion with Oracle DBAs | Low |  |  | Faster completion ETL jobs and timely availability of data to user | Work in Progress
b. Data archiving. Ihor discussed with business, waiting for business approval. Naresh to get list of tables with their max sizes – needed for archiving. Naresh to check AUDIT tables (load is taking between 7 to 8 hours). | Medium |  |  | Faster completion ETL jobs & Cube refresh and timely availability of data to user | Planned | Tables identified. Received approval from business.
c. Partitioning/re-org for big tables. | Low |  |  | Faster completion ETL jobs & Cube refresh and timely availability of data to user | Planned
a. Analyze LEO long running jobs and identify possible improvements | Low | 4 Incidents |  | Faster completion ETL jobs and timely availability of data to user | Planned
a. Analyze ANIMAS long running jobs and identify improvements | Low
a. Analyze SCO long running jobs and identify possible improvements | High | 4 Incidents |  | Faster completion ETL jobs and timely availability of data to user | Ongoing - 1 job tuned and moved to production
Raise Service request for receiving notification for long running tidal jobs. | High
Middle east processing | Low | 14 service requests |  | Reduction of around 25-30 hours of manual effort per month | Planned
Service account should be used in all shell scripts | Medium
Service account should be used in all report schedules | Medium | 2 Incidents |  | Avoid job failures and On time completion of jobs | Planned
Automated checks for file Visioncare | Low
Trident processing automation | High | 60 service requests | 04/07 - script is ready Testing is in progress | Reduction of around 20 hours of manual effort per month | Completed. Deployed in Production and monitoring in progress
Removal of unused reports and cubes | Medium | 101 reports removed |  | Increased space availability in the Cognos server. Reducing cube refresh failures due to space constraint | Ongoing
Create proper structure of folders in cognos for Diabetes | Medium | NA |  | Reduction in manual activity and easy navigation to the report location | Planned
Create documents for package paths,data sources, | Low | NA |  | Reduction in manual activity and easy navigation to the report data source | Work in progress
TIDAL_NAP Job Alert for: ITSUSRAW00564#LFSSP_DAS2 \ LFSJP533 had failed-Disable the job | Medium | 15-20 incidents |  | On Time completion and avoiding failures | Completed
ITSUSRABIP209#Perfect_Order_Delivery_LEO had failed - Find Root cause
TIDAL_NAP Job Alert for: ITSUSRABIP109#LIFE_MIGRTN_WW_Purchase_Price_Var_OV \ LIFE_MIGRTN_WW_Purchase_Price_Variance_Analysis_OV_PRD - Find Root cause | Medium | 1 Problem ticket |  | Avoid job failures and On time completion of jobs | Planned
Mapping sheet for all source,ETL , Target table and Cognos reports |  | 04/13 - one catalog done |  | Good Knowledge base | Work in Progress
TSA Automation | Medium | 4 service requests per month | 04/07 - Developing the script | Reduction of around 6-8 hours of manal effort | Work in progress
Sales and Marketing Automation | Medium | 1 service request per month |  | Reduction of around 4-6 hours of manal effort | Planned
SOP for frequent service requests | Medium | 5 Service Requests |  | Reduction in Service Requests | Planned
Knowledge Documents | Medium | NA |  | Knowledge Base | Work in progress
EMEA SSIS jobs improvement | Low | 1 Incident |  | Avoid job failure and On time completion of jobs | Planned
Track the hung jobs in the windows scheduler | Medium | 2-3 Incidents |  | Avoid job failure and On time completion of jobs | Work in progress
Sql queries for ETL jobs
Tidal schedule for Vision care ASPAC | Medium | NA |  | Efficient monitoring and Alert mechanism | Work in progress
ANIMAS emailing issue from Data Manager | Medium | 1 Problem ticket |  | Avoid job failure and On time completion of jobs | Completed

## BSC Canada & GBI (hidden)
Sr. No. | Date | Application Name | Opportunities/Initiatives | Effort Estimate (in hours) | Estimated Savings (Per year in hours) | Priority | Implementation Status | Assigned To | Comments
1 | 2017-01-27 | BSC Canada | Direct Job load was taking too long to complete causing SLA breach, support team worked with downstream system's support team to optimize the query. Reduces job execution time by 90%. It was used until Pharma migration complete. | 10 | 16 |  | Completed | Gopinath | This is performance enhancement activity. This resulted in a job running sooner helping us to not miss SLA
2 | 2017-01-28 | BSC Canada | SAP system sending duplicate records to the BSC system causing job to fail. Generic merge statement written to delete duplicate record. | 8 | 60 |  | Completed | Vibhas
3 | 2017-03-02 | BSC Canada | DB performance issues were causing BSC Canada to miss SLA on saturdays. Conflicting jobs running on Saturday were identified and rescheduled. Inaddition, DBA team was engaged in monitoring the database performance on multiple days to identify the root cause. DB server resources (Processors, Memory and SGA memory) were identified as the bottleneck and were increased to suit the load. | 10 | 60 |  | Completed | Gopinath | This is performance enhancement activity. This resulted in a job running sooner helping us to not miss SLA
4 | 2017-03-15 | BSC Canada | Documentation of kickout resolution | 10 | 40 |  | Completed | Vibhas/Bala | Prior documentation was not available for Kickout resolution process. Documenting the process resulted in availability of a quick reference guide eventually saving lot of time whenever kickouts need to be resolved.
5 | 2017-03-15 | BSC Canada | GST tool misc enhancements | 4 | 10 |  | Completed | Gopinath | The tool was originally developed by another team to transfer data to a downstream application. Following data integrity issues reported by the downstream application, issues with delimiters and file transfer were identified. Minor enhancements were done to the tool to send proper data and also support new environments setup by the downstream application.
6 | 2017-04-25 | BSC Canada | Discrepencies in historical sales numbers reported by Sales and Planning tool | 80 | 180 |  | In-Progress | Ashish | Business user reported data discrepencies in historical data (prioir to july 2016). Following RCA, the issue was identified to be with data issues caused by a data migration project performed aroud July 2016. Ashish has successfully tested the fix in QA environment. This code will be migrated to production soon to permanently fix the issue. The discrepency was causing the business user to manually perform few steps that would take atlest one hour a day till end of july in an year.
7 | 2017-04-30 | BSC Canada | Automation of Direct load status mails (for Consumer jobs) | 16 | 96 |  | In-Progress | Ashish | Direct load status mails are being sent out manually. Ashish is looking at updating an exisitng script to generate dashbaord in the format requested by business and setting it up on a event-based or time-based schedule to send automatic updates
8 | 2017-05-05 | GBI | EDW Dashboard needs to be manually prepared collecting data for each job separately through the Tidal Console. This is consuming significant time and effort on a daily basis. | 80 | 365 |  | In-Progress | Sathish/Nilanjan/Pandarinath
9 | 2017-06-30 | GBI | Manual ETA estimation | 80 | 104 |  | Planned | Sathish/Nilanjan/Pandarinath
10 | 2017-05-15 | GBI | Automation of manual activities related to SCG Trending Daily Activity are performed manually | 80 | 260 |  | In-Progress | Hemasundar/Pandarinath
11 | 2017-05-31 | GBI | Manual activities related to EDW Weekly immunology activity --> Executing the cubes IBM Cognos Transformer cubes from tidal. --> Moving of the mdc files into corresponding folders. --> Implementation of automation scripts for Backup process . | 40 | 208 |  | In-Progress | Hemasundar/Pandarinath

## JSC EDW (hidden)
Sr. No. | Date | Application Name | Opportunities/Initiatives | Effort Estimate (in hours) | Estimated Savings (Per year in hours) | Priority | Implementation Status | Assigned To | Comments
|  |  | Optimization done for long running jobs. There are eight jobs identified which had major bottleneck and been optimized. Query which was taking 40 minutes to execute now taking 2 minutes to complete. Reference JSC EDW weekly status report. Query efficiency is 20 to 30 times better now. | 40 hours | 132 | High | Completed
|  |  | No notification being sent in case of zero records are inserted in the EDW target table from source, we have written generic shell script which will take care of notification. Implementation is in QA | 40 Hours | NA | High | WIP |  | Implemented in QA
|  |  | Unix server (DEV, QA & PROD) unwanted files were causing space issue leading to Job failure, we have written shell script which will run once a week and cleanup unwanted file and release disk space on server. Implementation in DEV |  |  | High | WIP |  | Implemented in DEV
|  |  | When multiple workflow runs in parallel causing tidal job to fail due to param file issue, this issue was there in system for more than a year and we have come up with design and fix for it. This particular fix is not possible to test in DEV so we are migrating this change to QA and Prod after having approval. Expected to reduce 25 incidents an year. |  | Expected to reduce 25 incidents an year. | High | WIP |  | migrating this change to QA and Prod after having approval
|  |  | Finance Absorption application which Sogeti have started supporting since Feb had design issue, we setup call with Jennifer Boden (Sr. Financial Analyst) and apprised her the design issue. It was major bottleneck for busines user in uploading file and was leading to recurring incident. We have made a fix for the issue after having confirmation from Jennifer. Code migrated to QA. |  |  | High | WIP |  | Code migrated to QA.
|  |  | Preparation of GCC – Major Impact Management guide. Its created keeping in mind who all need to be reached out incase of global command center tickets raised and having loads of information about the application. Appreciated by pharma RSO Ajit (Email attached as reference) |  | NA | High
|  |  | SLT (Service Level Target) email automation. Database design is complete now we are in process of completing shell script to send email notification to the business user. |  |  | High
Health Check automation: Planned for automation manual work takes around two hour of time everyday

## Consumer Edge (hidden)
Sr. No. | Date | Application Name | Opportunities/Initiatives | Effort Estimate (in hours) | Estimated Savings (Per year in hours) | Priority | Implementation Status | Assigned To | Comments
POS manual download process is automated using Selenium web driver through Iron Python script. Automation is done for the following retailers. Reference is Portfolio review deck which is presented to Hima.  Amazon  Toysrus  CVS  Dollar General  Target  Kmart  Ecommerce (Mystore, Neutrogena, Rogaine)

## Global sales (hidden)
Sr. No. | Date | Application Name | Opportunities/Initiatives | Effort Estimate (in hours) | Estimated Savings (Per year in hours) | Priority | Implementation Status | Assigned To | Comments
EMEA load started taking more than 12 hours of time for populating 65000 records, nested SQL query was optimized and resultset we started getting in 20 minutes. Prior to optimization daily SLA breach was happening.
Year-end activities well documented and uploaded in sharepoint
Code change happened to address new business requirements well documented

## MyAcuvue (hidden)
Sr. No. | Date | Application Name | Opportunities/Initiatives | Effort Estimate (in hours) | Estimated Savings (Per year in hours) | Priority | Implementation Status | Assigned To | Comments
|  |  | End to end ETL average execution time is around 6Hrs 30 min; as the current scheduled start time is 4.00 AM SGT, the execution completes around 11.30 AM SGT. This is causing the MIRA reports users to wait for data till the execution completes. MyAcuvue_SFDC_S3_RS_Log_Monitor_Job_ITG_12_Misc MyAcuvue_SFDC_S3_RS_Log_Monitor_Job_ITG_EDW_Dim are identified as long running jobs and causing the delays. The underlying SQL’s of these jobs were optimized as per standard Tuning guidelines and also modified few of the DML operations without changing the functionalities. | 40 Hours | 1320 | High | Completed | Roy | . After the code fix implementations on Prod, the jobs execution time is expected to be reduced by 80% of the current execution duration. Due to this optimization, the Average time required to complete overall execution will be 1 hour as against the average time of 6 hours taken before optimization.
|  |  | The DIM tables loading pattern will be re-designed by changing the ETL jobs sequence to ensure that the Redshift Database resources are efficiently used. | 40 Hours | TBD | Low | Planned
|  |  | During full load, the size of the generated file which is transferred MBOX and to S3 for Redshift consumption is large. This was causing job to run long time and resulting in connection timeout. Plan is to split the File into multiplesmaller files. | 40 Hours | 25 | High | WIP |  | Under development in dev
|  |  | User Acces Audit : Review and Revoke access of non-myacuvue users in redshift | 24 Hours | NA | Medium | Completed |  | Only required users were provided access to Redshift

## General Improvement Ideas (hidden)
Source | Type | Opportunities/Initiatives | Comments
From RFP | ASO | Identify and reduce activities less or no value to engagement service delivery
From RFP | BP | Implement Application Support SOP | Implement Support Operations manual (SQP) Implement SOP for daily operational tasks Review SOP to identify Detective/Preventive Controls
| BP | Develop Application Maintenance Plan (Health Check) for critical applications | Develop AM Checklist (Weekly/Monthly)
| BP | Implement Application Users Audit (Quarterly)
From RFP | BP | Improve Application performance to reduce data load or report run time | Application optimization (Jobs, Reports, Tasks)
From RFP | BP | Use IRIS Known error Database(KEDB) to improve ticket MTTR
From RFP | ASO | Transfer L1.5/L2 activities to L1 team | Develop KA for L1 Support. KA to include Basic Application details, information to be captured before assigning ticket to support team Identify Tasks that can be handled by L1 Team (Password reset, unlock, user queries, report generation ect) Update KA Document and handover the Tasks
From RFP | ASO | Identify and Implement self service | Implement self service for application access management Implement self service for some of report requests Implement self service for some of Data requests
From RFP | ASO | Implement Application FAQs for user self service
From RFP | ASO | Reduce reoccurring incidents through Problem Mgmt. | Conduct FMA for Recurring Incidents Identify what needs to be fixed, enhanced, can be automated, what can be passed onto SD
From RFP | ASO | Reduce reoccurring service requests through automation, self help, enhancement etc. | Conduct FMA for Recurring SRs Identify what needs to be fixed, enhanced, can be automated, what can be passed onto SD
| ASO | Automate Manual tasks | Review SOP to Automate Manual tasks
From RFP | BP | Automate Application health checks
From RFP | BP | Implement batch job Re-start ability
From RFP | BP | Automate audit check for data delivery status/exception/errors
From RFP | ASO | Automate monitoring of Application, Database, Job, Reports, System processes)
From RFP | ASO | Automate data validation checks (data quality, integrity etc.)
From RFP | ASO | Automate log analysis and error/exception reporting
From RFP | BP | Automate periodic archiving / purging processes
Job Automation
From RFP | BP | Standardize communication, notifications etc. through support DLs
From RFP | BP | Standardize support process as per Support Playbook
From RFP | BP | Implement "ABC approval" process
From RFP | BP | Implement template for outage communication
|  | Problem management: Problem record to be created for each P1, P2 and critical issues | We can Create RCA Template and associate with KA Creation. KA will use the RCA template
|  | Change management : Every Change to Production environment must be approved | SR will be created with following details Change description, Change Requestor, Change Owner, Change Approver/Manager, Implementation Steps & Status. Gets approved by SLM/RSO
|  | RTP Process | Simplified checklist to Review and approve go-live from application perspective. Every Roll-Out will go through a Transition (Knowledge Capture/Shadow/Rev-Shadow) Process
From RFP | BP | Leverage JnJ enterprise tools(Solman, SCOM etc.) for Application and platform availability monitoring | URL monitoring, Service monitoring Identify what tools are available and what is implemented currently Identify Currently defined Thresholds Identfiy how alerts are communicated to whom
From RFP | BP | Leverage JnJ enterprise tools(Tidal etc.) for job scheduling and monitoring | Job Monitoring Identify what tools are available and what is implemented currently Identify Currently defined Thresholds Identfiy how alerts are communicated to whom
From RFP | BP | Leverage JnJ enterprise tools(Solman, Netcool etc.) for performance monitoring | disk space monitoring, CPU/Memory utilization monitoring, NW Bandwidth (Database/OS/Web Servers/Apps Servers/Middleware) Identify what tools are available and what is implemented currently Identify Currently defined Thresholds Identfiy how alerts are communicated to whom
From RFP | BP | Integrate existing monitoring tools with service management tools ( IRIS, Solman)
|  | IRIS Configuration | Are all Apps Using IRIS, alert configuration for status change, groups properly created
From RFP | ASO | Transfer All activities that can be serviced from offshore
From RFP | ASO | Optimize support effort through cross training
From RFP | ASO | Consolidate L1.5 services across teams | Phase 1 : small apps with same technology grouped and implement AMOS, AMTS, AMSS structure; Phase 2 : AMOS across apps, AMTS and AMSS specific to Apps
From RFP | ASO | Consolidate teams based on similar technology services
From RFP | ASO | Implement shared service across teams
From RFP | ASO | Optimize Service management effort
From RFP | ASO | Amend SOW to carve out Project/Enhancement $
From RFP | ASO | Optimize Support Coverage Window as per Business need
From RFP | ASO | Optimize SLAs as per Application Criticality
Governance model with clear R&R
SLM (Onsite/Offshore) & RSO alignment
|  | CORE Team | Form a CORE Team to do Incident Analysis, Problem Management, Change Management, Critical Issue Handling
Town-Hall every month..Azfar addressing the team
Daily dash-board
|  | Weekly review (Internal) : | Resource Status, Incident Status, high-lights and low lights, Improvement plan tracker, other items of concerns
Capacity Planning
Identify resource knowledge gaps and plan for training
|  | Training : | ITIL foundation certified, weekly class room training, ITSM training; Educate team on priorities, SLAs; Knowledge sharing on recent issues; Training on JnJ Business Process/Domain
Develop SMEs in widely used technology and domain
|  | Define and Implement KM Framework | General : Contracts/Sow, RFP, Process Artifacts/templates; Application Specific : Business, Technology (beginner, intermediate, advanced) IRIS : KA
|  | Review of Infrastructure: | Current capacity review and planning
|  | Access controls of OS/DB/App/Middleware to be reviewed : | User ID details to be extracted, Validate the IDs and identify the Owners, Generic IDs to be disabled (Non service accounts), All service account IDs password to be restricted/vaulted
Preventive maintenance calendar to be created for DB servers, application servers
Back up policy, Purging & archival policy for each application
Dedicated Dev & QA Server for Testing Production changes

## ASO 2017 - Completed
Region | GOC | Application Name | Lever | AUTOMATION BUCKET | Category | Sr. No. | ASO Owner | Opportunities/Initiatives | Planned Completion Date | Assigned To | Implementation Effort (in hours) | Estimated Savings (Per year in hours) | Actual Hours Before Implementation | Actual Hours After Implementation | Actual Savings (Per year in hours) | Ticket Reduction/Month | Implementation Status | Comments | % Completed
NA | PHARMA | IQLIK | Performance tuning | PERF.TUNING | ASO |  | Vibhas/Hamza | RDT Renumbering for all TAs | August 22nd | IQLIK Team | 60 | 416 |  |  |  |  | Completed
NA | CMT | JJDCC | Process Improvement | BEST PRACTICE | BEST PRACTICES | 4 | Vinod/Raj | Oracle Auto stat is enabled, need to see if we can move auto stat window. Ihor to initiate discussion with Oracle DBAs | 2017-03-01 | Naresh/Biswaranjan | 10 | 0 | 0 | 0 | 0 |  | Completed | Faster completion ETL jobs and and this is associated to the items in Row 60 and 61
NA | CMT | JJDCC | Process Improvement | BEST PRACTICE | BEST PRACTICES | 11 | Vinod/Raj | Removal of unused reports and cubes(total 1000+) | Q2/Q3/Q4 | Santosh/Charan | 100 | 0 | 0 | 0 | 0 |  | Completed | 06/22/2017- 06/19/2017-No further update on this week. 06/12/2017-120 report identified. and removed 100 reports removed. Increased space availability in the Cognos server. Reducing cube refresh failures due to space constraint 05/04/2017 - Santosh need to discuss with Vinod 101 reports removed. Increased space availability in the Cognos server. Reducing cube refresh failures due to space constraint
NA | CMT | MIRA | Tools-Monitoring/Alerting/Job Scheduling | BEST PRACTICE | ASO | 25 | Vibhas/Raj | Modify the alert for high CPU utilization : If CPU utilization alarm is reduced from 1hr to 30 minutes, it will save 30 mins in each outage. | 2017-07-01 | Sourav | 10 | 30 | 60 |  |  | NA | completed
ASPAC | CMT | MIRA | Tools-Monitoring/Alerting/Job Scheduling | BEST PRACTICE | ASO | 26 | Vibhas/Raj | Modify the alert for high CPU utilization : If CPU utilization alarm is reduced from 1hr to 30 minutes, it will save 30 mins in each outage. | 2017-07-01 | Sourav | 10 | 30 | 60 |  |  | NA | completed
LSGPS | CMT | MIRA | Tools-Monitoring/Alerting/Job Scheduling | BEST PRACTICE | ASO | 27 | Vibhas/Raj | Modify the alert for high CPU utilization : If CPU utilization alarm is reduced from 1hr to 30 minutes, it will save 30 mins in each outage. | 2017-07-01 | Sourav | 10 | 30 | 60 |  |  | NA | Completed
NA | CMT | MIRA | Process Standardization | BEST PRACTICE | BEST PRACTICES | 56 | Vibhas/Raj | Segregation of tickets based on region and environment. There was no separate configuration item in IRIS for dev and qa so all ticket by default was assigned to production configuration item in IRIS. It helps identifiying environment | 2017-09-01 | Raghavendra | 10 | 0 | 0 |  |  | NA | Completed |  | 10%
ASPAC | CMT | myAcuvue | Technical Debt Reduction | BEST PRACTICE | BEST PRACTICES | 4 | Shivakumar | User Acces Audit : Review and Revoke access of non-myacuvue users in redshift | 2017-03-01 | Roy | 24 | 0 | 0 | 0 | 0 | NA | Completed
NA | PHARMA | JSC EDW | Technical Debt Reduction | BEST PRACTICE | BEST PRACTICES |  | Vibhas/Hamza | Changes to /tmp folder: INFA Admin team raised a concern to move all JSC related files from /tmp to Project /TEMP folder due to space constraints. Team made changes to exiting design to point all the temporary files in INFA TEMP folder instead of /tmp . | October | JSCEDW Team | 40 | 0 | 0 | 0 | 0 | NA | Completed
NA | PHARMA | Global Pricing | Technical Debt Reduction | BEST PRACTICE | BEST PRACTICES |  |  | Bit bucket implementation. | 1-Oct- 2017. | Global Pricing Team | 84 | [5 empty] | Completed
NA | PHARMA | Janssen Connect | Technical Debt Reduction | BEST PRACTICE | BEST PRACTICES |  |  | Bit bucket implementation. | 4-Oct- 2017. | Janssen Connect Team | 84 | 0 | 0 | 0 |  |  | Completed
NA | CONSUMER | BSC Canada | Performance tuning | PERF.TUNING | ASO | 1 | Prashanth M/Sidra | Direct Job load was taking too long to complete causing SLA breach, support team worked with downstream system's support team to optimize the query. Reduces job execution time by 90%. It was used until Pharma migration complete. | 2017-03-01 | Prashanth M | 10 | 21.25 | 22.5 | 1.25 | 21.25 | NA | Completed | This is performance enhancement activity. This resulted in a job running sooner helping us to not miss SLA
NA | CONSUMER | BSC Canada | Performance tuning | PERF.TUNING | ASO | 8 | Prashanth M/Sidra | Correcting the table space issue causing job delays | 2017-08-01 | Ashish | 40 | 468 | 1248 | 780 | 468 | ? | Completed | In BSC Canada Consumer Application, there were 4 Tables (Oracle) which were occuoying 2 TB of space (actual size was 52 GB). This was causing the related jobs to either fail or taake longer time. Team did the analysis and found a way with help of DBA team to compress the table by removing empty space (using MOVE ONLINE Command)
NA | CONSUMER | Global sales | Performance tuning | PERF.TUNING | ASO | 1 | Vibhas/Sidra | EMEA load started taking more than 12 hours of time for populating 65000 records, nested SQL query was optimized and resultset we started getting in 20 minutes. Prior to optimization daily SLA breach was happening. | 2017-03-01 | Pawan/Aditi | 24 | 390 | 390 | 0 | 390 | NA | Completed
NA | CMT | JJDCC | Performance tuning | PERF.TUNING | BEST PRACTICES | 27 | Vinod/Raj | Sco tuning - Analyze schema s2g_star weekly once | 2017-06-01 | Rehana | 36 | 0 | 0 | 0 | 0 |  | Completed | 06/19/2017-Completed
NA | CMT | JJDCC | Performance tuning | PERF.TUNING | ASO | 25 | Vinod/Raj | SCO Tuning--S2GN_material_Scarp_J | 2017-06-01 | Biswa | [5 empty] | NA | completed | 06/22/2017- 06/12/2017-Analysing the query which taking more time. ETA is 06/23/2017
NA | CMT | JJDCC | Performance tuning | PERF.TUNING | ASO |  | Vinod/Raj | Sco tuning - S2G_CUSTOMER_BASE_PRICE_AUDIT_J | 2017-06-01 | Rehana | [5 empty] | NA | completed | 06/22/2017-An incident is raised for DBA Team. 06/19/2017-Rehana will confirm the ETA on 06/22/2017
NA | CMT | JJDCC | Performance tuning | PERF.TUNING | ASO | 25 |  | S2GN_CAPEX_LOAD_J | 2017-07-01 | Naresh/Rehana | 10 | 60 |  |  |  | ? | Completed | 05/25/2017--It moved to production.No job failure till now | 100%
NA | CMT | JJDCC | Performance tuning | PERF.TUNING | ASO | 8 | Vinod/Raj | Analyze SCO long running jobs and identify possible improvements (Ongoing) | 2017-09-01 | Naresh/Biswa | 75 | 40 | 40 |  |  | 4 | completed | 4 Incidents. Faster completion ETL jobs and timely availability of data to user 05/11/2017--GSS_RUN_AUDIT_J--two builds identified.currently the job is running for around 5 hours. Waiting for Iris approval to move the changes into production. 05/25/2017--Identified the long running jobs Preparing a technical document to move the changes in production
NA | CMT | JJDCC | Performance tuning | PERF.TUNING | ASO | 26 | Vinod/Raj | S2GN_DAILY_SUMMARY_J | 2017-09-01 | Anand | [5 empty] | NA | completed | 06/22/2017- 06/19/2017--Anand will complete on or before 06/27/2017 06/15/2017 - Identified the sub jobs that have to be tuned. Working on query tuning. 06/12/2017 - Analysing the Sub Jobs in the main job. ETA is 23/06/2017
NA | PHARMA | JSC EDW | Performance tuning | PERF.TUNING | ASO | 1 | Vibhas/Hamza | Optimization done for long running jobs. There are eight jobs identified which had major bottleneck and been optimized. Query which was taking 40 minutes to execute now taking 2 minutes to complete. Reference JSC EDW weekly status report. Query efficiency is 20 to 30 times better now. | 2017-04-01 | Madhav M | 40 | 167.2 | 176 | 8.8 | 167.2 | NA | Completed
NA | PHARMA | JSC EDW | Performance tuning | PERF.TUNING | ASO |  | Vibhas/Hamza | Optimizing DBL Informatica long running jobs | 2017-12-01 | Ramakrishna |  | 132 | 132 | 0.2 | 131.8 | NA | Completed
NA | PHARMA | JSC EDW | Performance tuning | PERF.TUNING | ASO |  | Vibhas/Hamza | PDP long running jobs ( F STDY ) optimization | 2017-12-01 | Ramakrishna |  | 374 | 396 | 22 | 374 | NA | Completed
NA | PHARMA | JSC EDW | Performance tuning | PERF.TUNING | ASO |  | Vibhas/Hamza | PDP API large info link query (Spotfire) optimization | 2017-12-01 | Ramakrishna |  | 132 | 132 | 0.23 | 131.77 | NA | Completed
ASPAC | CMT | MIRA | Process Improvement | PERF.TUNING | ASO | 15 | Vibhas/Raj | Optimize ASPAC NSD deep dive dash board within shorter | 2017-05-01 | Anil | 30 |  | 1440.6 | 411.6 | 1029 | NA | Completed | 05/24 - Awaiting user confirmation | 100%
LSGPS | CMT | MIRA | Performance tuning | PERF.TUNING | ASO | 21 | Vibhas/Raj | Optimize LifeScan GPS ETL to run multiple downloads from MBOX in parallel | 2017-07-01 | Muthu | 16 | 16 | 18 |  |  | 2 | Completed | This is performance optimization. Savings: 25 mins per job run when executed manually when failed; approx 2 failures in a month | 90%
NA | CMT | MIRA | Process Improvement | PERF.TUNING | ASO | 9 | Vibhas/Raj | Template for regression suite | 2017-04-01 | Rishiraj | 16 | 3 | 3 | 0 | 3 | NA | Completed | On an average, there are 3 major version updates for every iOS version; 3 times creation of testing suite will take 1 hour each | 100%
ASPAC | CMT | myAcuvue | Performance tuning | PERF.TUNING | ASO | 1 | Shivakumar | End to end ETL average execution time is around 6Hrs 30 min; as the current scheduled start time is 4.00 AM SGT, the execution completes around 11.30 AM SGT. This is causing the MIRA reports users to wait for data till the execution completes. MyAcuvue_SFDC_S3_RS_Log_Monitor_Job_ITG_12_Misc MyAcuvue_SFDC_S3_RS_Log_Monitor_Job_ITG_EDW_Dim are identified as long running jobs and causing the delays. The underlying SQL’s of these jobs were optimized as per standard Tuning guidelines and also modified few of the DML operations without changing the functionalities. | 2017-04-01 | Roy | 40 | 1320 | 1716 | 396 | 1320 | NA | Completed
ASPAC | CMT | myAcuvue | Technical Debt Reduction | PERF.TUNING | ASO | 3 | Shivakumar | During full load, the size of the generated file which is transferred MBOX and to S3 for Redshift consumption is large. This was causing job to run long time and resulting in connection timeout. Plan is to split the File into multiplesmaller files. | 2017-05-01 | Roy | 40 | 0 | 0 | 0 | 0 | 1 | Completed | This happens only during full load. Estimated to do 4 full loads per year.
NA | PHARMA | JSC EDW | Performance tuning | PERF.TUNING | ASO |  | Vibhas/Hamza | EMS Scheduling: As part of EMS Integration to Databeat project performance issues batch completion delayed daily around 3-4 hours. Team analyzed the scheduling and made changes to existing schedules through which we avoided batch delays | October | JSCEDW Team | 10 | 24 | 0 | 0 | 0 | NA | Completed
NA | ALL | ALL | Automation | SMART ANALYTICS-Manual | ASO | 16 | Vibhas/Raj | Automation SLT email notification | 2017-07-01 | Shekar | 240 | 1800 | 21 |  |  | NA | Completed | 5 min per email/Post implementation 0 mins
NA | CONSUMER | BSC Canada | Automation | SMART ANALYTICS-Manual | ASO | 7 | Prashanth M/Sidra | Automation of Indirect load status mails (for Consumer jobs) | 2017-05-01 | Ashish | 16 | 96 | 96 | 0 | 96 | NA | Completed | Indirect load status mails are being sent out manually. Ashish is looking at updating an exisitng script to generate dashbaord in the format requested by business and setting it up on a event-based or time-based schedule to send automatic updates
NA | PHARMA | GBI | Automation | SMART ANALYTICS-Manual | ASO | 52 | Prashanth M/ Hamza | Dashboard needs to be made manually collecting data for each job separately through the Tidal Console - EDW | 2017-06-01 | Team | 80 | 120 | 0 | 0 | 0 | NA | Completed | Testing is in progress for the following activity
LSGPS | CMT | MIRA | Automation | Automation-Others | ASO | 18 | Vibhas/Raj | Trigger jobs only when files are available (LFSCGPS) | 2017-07-01 | Muthu | 60 | 720 | 720 |  |  | 1 | completed | each region requires 1hr/day to monitor | 50%
NA | CMT | JJDCC | Automation | Automation-Others | ASO | 1 | Vinod/Raj | Trident processing automation | 2017-03-01 | Nageswara Rao | 60 | 540 | 570 | 30 | 540 | NA | Completed | 60 service requests. Reduction of around 20 hours of manual effort per month
NA | CONSUMER | Consumer Edge | Automation | SMART ANALYTICS-Manual | ASO | 2 | Vibhas/Sidra | Portal Health Check Automation in .NET | 2017-07-01 | Jit | 40 | 520 | 520 |  |  | NA | Completed
LSGPS | CMT | MIRA | Automation | Automation-Others | ASO | 23 | Vibhas/Raj | ETL package to add and update multiple users LSGPS | 2017-08-01 | Kavya | 24 | 96 | 120 |  |  | NA | Completed | Savings: 1 hr/request; approx 8 tickets per month | 20%
ASPAC | CMT | MIRA | Automation | Automation-Others | ASO | 22 | Vibhas/Raj | ETL package to add and update multiple users ASPAC | 2017-07-01 | Kavya | 24 | 96 | 120 |  |  | NA | Completed | Savings: 1 hr/request; approx 8 tickets per month | 20%
ASPAC | CMT | MIRA | Automation | Automation-Others | ASO | 10 | Vibhas/Raj | Alert when application is down (ASPAC Region) : It will intimate support Team through mail whenever MSTR application goes down inside the server. | 2017-06-01 | Sourav | 10 | 40 | 40 |  |  | NA | Completed | It will save around 1 hr per outage. | 100%
LSGPS | CMT | MIRA | Automation | Automation-Others | ASO | 11 | Vibhas/Raj | Alert when application is down (LSGPS Region) : It will intimate support Team through mail whenever MSTR application goes down inside the server. | 2017-06-01 | Sourav | 10 | 40 | 40 |  |  | NA | Completed | It will save around 1 hr per outage. | 100%
NA | CMT | MIRA | Automation | Automation-Others | ASO | 12 | Vibhas/Raj | Alert when application is down (NA Region) : It will intimate support Team through mail whenever MSTR application goes down inside the server. | 2017-05-01 | Sourav | 20 | 40 | 40 |  |  | NA | Completed | It will save around 1 hr per outage | 100%
NA | PHARMA | JSC EDW | Automation | Automation-Others | ASO | 3 | Vibhas/Hamza | Unix server (DEV, QA & PROD) unwanted files were causing space issue leading to Job failure, we have written shell script which will run once a week and cleanup unwanted file and release disk space on server. Implementation in DEV | 2017-07-01 | Krishna B | 20 | 72 | 72 |  |  | 1 | Completed | Implemented in DEV
| PHARMA | JSC EDW | Automation | Automation-Others | ASO |  | Vibhas/Hamza | Unix space estimation : An automated script to check the space available in Unix file system and send an alert email if the space crosses the threshold value. | 2017-12-01 | Ramakrishna |  | 0 | 0 | 0 | 0 | 0 | Completed
ASPAC | CMT | MIRA | Automation | Automation-Others | ASO | 4 | Vibhas/Raj | Automation MSTR cache deletion - ASPAC and Japan | 2017-03-01 | Rishiraj & Shekar | 40 | 41.66 | 41.66 | 0 | 41.66 | NA | Completed | time for monitoring + manual deletion of cache (yearly) estimation only numbers put in comments the explanation 5 mins wait time + 5 mins cache clearing | 100%
LSGPS | CMT | MIRA | Automation | Automation-Others | ASO | 5 | Vibhas/Raj | Automation MSTR cache deletion - LifeScan EMEA | 2017-04-01 | Rishiraj & Shekar | 24 | 41.66 | 41.66 | 0 | 41.66 | NA | Completed | Same as above | 100%
NA | CMT | MIRA | Automation | Automation-Others | ASO | 20 | Vibhas/Raj | Automation MSTR cache deletion - NA | 2017-07-01 | Rishiraj & Shekar | 24 | 42 | 42 |  |  | 20 | Completed | Same as above | 50%
NA | CMT | MIRA | Automation | Automation-Others | ASO | 44 | Vibhas/Raj | Avoid JVM Heap Size Error : Currently we are receivie alert message for Max Heap size error. It can be stopped by archiving the log. | 2017-09-01 | Sourav | 20 | 65 | 65 |  |  | NA | Completed |  | 0%
NA | CONSUMER | Consumer Edge | Automation | SMART ANALYTICS-Manual | ASO | 1 | Vibhas/Sidra | POS manual download process is automated using Selenium web driver through Iron Python script. Automation is done for the following retailers. Amazon, Toysrus, CVS, Dollar General, Target, Kmart, Ecommerce (Mystore, Neutrogena, Rogaine) | 2016-12-01 | Meenal G | 300 | 416 | 416 | 0 | 416 | NA | Completed
NA | CONSUMER | Consumer Edge | Automation | SMART ANALYTICS-Manual | ASO | 3 | Vibhas/Sidra | Cognos Monthly Report Automation | 2017-07-01 | Suresh N | 60 | 12 | 12 | 0 | 12 | 1 | Completed
NA | PHARMA | GBI | Automation | SMART ANALYTICS-Manual | ASO | 3 | Prashanth M/Hamza | Automation of manual activities related to SCG Trending Daily Activity are performed manually | 2017-07-01 | Hemasundar/Pandarinath | 80 | 260 | 260 |  |  | NA | Completed
NA | CMT | JJDCC | Process Improvement | SMART ANALYTICS-Manual | ASO | 21 | Vinod/Raj | Track the hung jobs in the windows scheduler | 2017-06-01 | Lokesh | 20 | 50 | 50 |  |  | 3 | Completed | 2-3 Incidents. Avoid job failure and On time completion of jobs 05/11/2017--Completed | 100%
ASPAC | CMT | MIRA | Automation | SMART ANALYTICS-Manual | ASO | 8 | Vibhas/Raj | ASPAC Japan Sunday job schedule | 2017-04-01 | Shekar | 16 | 208 | 208 | 0 | 208 | 4 | Completed | Job runs on Sun & Mon; Savings: 4 hrs per week | 100%
NA | CMT | MIRA | Automation | SMART ANALYTICS-Manual | ASO | 7 | Vibhas/Raj | Automate Vistakon NA SSIS project version switch over | 2017-04-01 | Shekar | 16 | 132 | 132 | 0 | 132 | NA | Completed | Savings: 30mins/day, 5 days per week | 100%
NA | CMT | MIRA | Automation | SMART ANALYTICS-Manual | ASO | 6 | Vibhas/Raj | automation of cube refresh for my acuvue | 2017-04-01 | Ramya | 16 | 91.25 | 547.5 | 456.25 | 91.25 | NA | Completed | Savings: 15mins/day | 100%
ASPAC | CMT | MIRA | Automation | SMART ANALYTICS-Manual | ASO | 48 | Vibhas/Raj | Automation of Year End Activities (ASPAC, NA & LSGPS) | December | Shekar | 40 | 150 |  |  |  | 5 | Completed | 5 incidents last year since periodic tables were not updated
NA | PHARMA | IQLIK | Automation | SMART ANALYTICS-Manual | ASO |  | Vibhas/Hamza | Manual Monitoring of Task failures in QLIKSENSE | August 22nd | IQLIK Team | 10 | 78 |  |  |  |  | Completed
NA | PHARMA | IQLIK | Automation | SMART ANALYTICS-Manual | ASO |  | Vibhas/Hamza | Validation Automation | Mid November | IQLIK Team | 120 Hrs | 360 |  |  |  | 48 | completed
NA | PHARMA | Global Pricing | Automation | SMART ANALYTICS-Manual | ASO |  |  | Manual monitoring of task failures. | Aug-2017 | Global Pricing Team | 70 | 260 |  |  |  |  | Completed
NA | PHARMA | Janssen Connect | Automation | SMART ANALYTICS-Manual | ASO |  |  | Manual monitoring of task failures. | Aug-2017 | Janssen Connect Team | 70 | 260 |  |  |  |  | Completed
NA | CONSUMER | BSC Canada | Lean and process optimization | SMART ANALYTICS-REC INC | ASO | 2 | Prashanth M/Sidra | SAP system sending duplicate records to the BSC system causing job to fail. Generic merge statement written to delete duplicate record. | 2017-03-01 | Vibhas | 8 | 60 | 70 | 10 | 60 | 1 | Completed | 1 incident per month
NA | CONSUMER | BSC Canada | Lean and process optimization | SMART ANALYTICS-REC INC | ASO | 3 | Prashanth M/Sidra | DB performance issues were causing BSC Canada to miss SLA on saturdays. Conflicting jobs running on Saturday were identified and rescheduled. Inaddition, DBA team was engaged in monitoring the database performance on multiple days to identify the root cause. DB server resources (Processors, Memory and SGA memory) were identified as the bottleneck and were increased to suit the load. | 2017-04-01 | Prashanth M | 10 | 60 | 108 | 48 | 60 | NA | Completed | This is performance enhancement activity. This resulted in a job running sooner helping us to not miss SLA
NA | CONSUMER | BSC Canada | Lean and process optimization | SMART ANALYTICS-REC INC | ASO | 5 | Prashanth M/Sidra | GST tool misc enhancements | 2017-04-01 | Prashanth M | 4 | 10 | 10 | 0 | 10 | 1 | Completed | The tool was originally developed by another team to transfer data to a downstream application. Following data integrity issues reported by the downstream application, issues with delimiters and file transfer were identified. Minor enhancements were done to the tool to send proper data and also support new environments setup by the downstream application.
NA | CONSUMER | BSC Canada | Lean and process optimization | SMART ANALYTICS-REC INC | ASO | 6 | Prashanth M/Sidra | Discrepencies in historical sales numbers reported by Sales and Planning tool | 2017-05-01 | Ashish | 80 | 180 | 180 | 0 | 180 | 1 | completed | Business user reported data discrepencies in historical data (prioir to july 2016). Following RCA, the issue was identified to be with data issues caused by a data migration project performed aroud July 2016. Ashish has successfully tested the fix in QA environment. This code will be migrated to production soon to permanently fix the issue. The discrepency was causing the business user to manually perform few steps that would take atlest one hour a day till end of july in an year.
NA | CMT | JJDCC | Process Improvement | SMART ANALYTICS-REC INC | ASO | 10 | Vinod/Raj | Service account should be used in all shell scripts & report schedules | Q3 | Santosh/Anand | 20 | 60 | 60 |  |  |  | Completed | 06/22/2017-anand raised the request yesterday.Today or tomorrow we will get the permanet access. 06/19/2017-Anand will check with window team for all access. 06/15/2017- Service account and password have been shared by Ihor. We requested and gotaccess to all servers. Updating the jobs to run with service account is in progress. 06/12/2017-Santhosh will raise the service request today 05/25/2017-Ihor shared service account user name & password. Team need to identify the scripts & schedule to change the service account.
NA | CMT | JJDCC | Process Improvement | SMART ANALYTICS-REC INC | ASO | 22 | Vinod/Raj | ANIMAS emailing issue from Data Manager | 2017-03-01 | Naresh | 10 | 72 | 72 | 0 | 72 | 20 | Completed | 1 Problem ticket. Avoid job failure and On time completion of jobs
NA | CMT | JJDCC | Process Improvement | SMART ANALYTICS-REC INC | ASO | 15 | Vinod/Raj | Job Failure: Perfect_Order_Non-Revenue_PRD | 2017-06-01 | Anand | 10 | 60 | 60 |  |  | 4 | Completed | 05/11/2017--Anand will complete by tomorrow 05/25/2017--Completed & running fine in production | 100%
| CMT | JJDCC | Process Improvement | SMART ANALYTICS-REC INC | ASO | 17 | Vinod/Raj | Job Failure: LFSJP1034_TEN | 2017-06-01 | Rehana | 10 | 60 | 60 |  |  | 4 | Completed | 05/29/2017-Completed | 100%
NA | CMT | JJDCC | Lean and process optimization | SMART ANALYTICS-REC INC | ASO | 16 | Vinod/Raj | Job Failure: LIFE_MIGRTN_WW_Purchase_Price_Variance_Analysis_OV_PRD | 2017-07-01 | Charan/Biswa | 10 | 60 | 60 |  |  | 4 | Completed | 06/22/2017-you resudle the job to run every saterday. 1 Problem ticket. Avoid job failures and On time completion of jobs 05/25/2017--Analysing the issue at the cube level. 05/29/2017-- Identifying the cubes which are running at the sametime and checking the db with their log files 06/12/2017-created a new job schedule. 06/15/2017 - Job is not running as per schedule, Requested to scheduling L2 team to schedule the job as per our request.
NA | PHARMA | JSC EDW | Lean and process optimization | SMART ANALYTICS-REC INC | BEST PRACTICES | 2 | Vibhas/Hamza | No notification being sent in case of zero records are inserted in the EDW target table from source, we have written generic shell script which will take care of notification. Implementation is in QA | 2017-04-01 | Manjunath C | 40 | 0 | 0 | 0 | 0 | 1 | Completed | avoiding potential escalation. MRR report michael Syntax
NA | PHARMA | JSC EDW | Lean and process optimization | SMART ANALYTICS-REC INC | ASO | 5 | Vibhas/Hamza | Finance Absorption application which Sogeti have started supporting since Feb had design issue, we setup call with Jennifer Boden (Sr. Financial Analyst) and apprised her the design issue. It was major bottleneck for busines user in uploading file and was leading to recurring incident. We have made a fix for the issue after having confirmation from Jennifer. Code migrated to QA. | 2017-05-01 | Keerthana | 24 | 60 | 60 |  |  | 5 | completed | expected to reduce 5 incidents per month
NA | PHARMA | JSC EDW | Lean and process optimization | SMART ANALYTICS-REC INC | ASO | 4 | Vibhas/Hamza | When multiple workflow runs in parallel causing tidal job to fail due to param file issue, this issue was there in system for more than a year and we have come up with design and fix for it. This particular fix is not possible to test in DEV so we are migrating this change to QA and Prod after having approval. Expected to reduce 25 incidents an year. | 2017-07-01 | Krishna B | 80 | 75 | 75 |  |  | 2 | Completed | Expected to reduce 25 incidents an year.
NA | PHARMA | JSC EDW | Automation | SMART ANALYTICS-REC INC | ASO |  | Vibhas/Hamza | We have observed in MATL_TYPE table that update date is less than the create date.We are working on interchanging the both th columns and pull all the data which has already enetred to respective columns. | August | Shruti Hegde | 40 | [5 empty] | Completed | Analysis is in progress
NA | CMT | JJDCC | Process Improvement | SMART ANALYTICS-REC INC | ASO | 14 | Vinod/Raj | TIDAL_NAP Job Alert for: ITSUSRAW00564#LFSSP_DAS2 \ LFSJP533 had failed-Disable the job | 2017-03-01 | Naresh | 5 | 60 | 60 | 0 | 60 | 2 | Completed | 15-20 incidents. On Time completion and avoiding failures
NA | CONSUMER | Consumer Edge | Automation | SMART ANALYTICS-SR | ASO | 1 | Vibhas/Sidra | POS Data sync from Prod to QA | 2017-07-01 | Jit | 40 | 312 | 312 |  |  | NA | Completed | In DEV. BUIt Review pending
NA | PHARMA | JSC EDW | Automation | SMART ANALYTICS-SR | ASO | 7 | Vibhas/Hamza | created a script to automate the deletion of old/unwanted files in QV folder which deletes the files older than 15 days. The script will run daily, finds the 15 days older file and deletes it. The QV folder would consume more than 100GB of space.Now the space isse is resolved. | 2017-07-01 | Shruti Hegde | 80 | 50 | 50 | 0 |  | NA | Completed | space issue is resolved | 100%
ASPAC | CMT | MIRA | Automation | SMART ANALYTICS-SR | ASO | 1 | Vibhas/Raj | Automation of user creation in MSTR in ASPAC | 2017-03-01 | Rishiraj | 10 | 96 | 120 | 24 | 96 | NA | Completed | - 5 user requests per month/60 per year/ current- 10 min per user/Post implementation - 2 mins per user | 100%
LSGPS | CMT | MIRA | Automation | SMART ANALYTICS-SR | ASO | 2 | Vibhas/Raj | Automation of user creation in MSTR in EMEA | 2017-03-01 | Rishiraj | 10 | 96 | 120 | 24 | 96 | NA | Completed | - 5 user requests per month/60 per year/ current- 10 min per user/Post implementation - 2 mins per user | 100%
NA | CMT | MIRA | Automation | SMART ANALYTICS-SR | ASO | 3 | Vibhas/Raj | Automation of user creation in MSTR in NA | 2017-03-01 | Rishiraj | 10 | 96 | 120 | 24 | 96 | NA | Completed | - 5 user requests per month/60 per year/ current- 10 min per user/Post implementation - 2 mins per user | 100%
NA | CMT | MIRA | Automation | SMART ANALYTICS-SR | ASO | 50 | Vibhas/Raj | Environment Sync -> creation of ETL to load data from PROD to QA -- NA | 2017-07-01 | Shankar | 16 | 48 | 48 | 12 | 36 | NA | Completed | Savings: 3 hr for each sync; approx 1 env sync requests per month due to data mismatch between prod & qa | 75%
LSGPS | CMT | MIRA | Automation | SMART ANALYTICS-SR | BEST PRACTICES |  | Vibhas/Raj | Notify users on age of the files in MBOX (90 Days) | August | Muthu | 24 | [5 empty] | Completed
ASPAC | CMT | MIRA | Automation | SMART ANALYTICS-SR | BEST PRACTICES |  | Vibhas/Raj | Send notification once ASPAC, LSGPS, NA disk-space is 85% reached | 2017-08-01 | Shankar | 16 | 0 |  |  |  | NA | Completed
Note on N26: Natarajan, Shankar [ITSUS Non-J&J]: 3.5 mins - 98 users - per day - 252 working days divided by hours (3.5 * 98/ 60 )*252 Excluding Japan Users
Note on O26: Natarajan, Shankar [ITSUS Non-J&J]: 1 mins - 98 users - per day - 252 working days divided by hours (1 * 98 / 60 )*252

## ASO Master List - 2018
Region | GOC | Application Name | Lever | AUTOMATION BUCKET | Category | Sr. No. | ASO Owner | Opportunities/Initiatives | Planned Completion Date | Assigned To | Implementation Effort (in hours) | Estimated Savings (Per year in hours) | Actual Hours Before Implementation | Actual Hours After Implementation | Actual Savings (Per year in hours) | Ticket Reduction/Month | Implementation Status | Comments | % Completed
NA | PHARMA | IQLIK | ? | ? | ASO |  | Vibhas/Hamza | DCA Service Improvement | Nov 17th | IQLIK Team | 30 Hrs | 26 Hrs |  |  |  |  | In Progress
NA | CMT | JJDCC | Process Improvement | BEST PRACTICE | BEST PRACTICES | 5 | Vinod/Raj | Data archiving. Ihor discussed with business. Received approval to archieve data prior to 2010. Identified the tables for archieving. | Q3 | Biswaranjan/Naresh | 50 | 0 | 0 | 0 | 0 |  | On-Hold | Faster completion ETL jobs & Cube refresh and timely availability of data to user. 05/11/2017--Tables have been identified. Need to start work on this. 06/01/2017--Will start next week
NA | CMT | JJDCC | Process Improvement | BEST PRACTICE | BEST PRACTICES | 6 | Vinod/Raj | Partitioning/re-org for big tables. | Q3/Q4 | Biswaranjan | 20 | 0 | 0 | 0 | 0 |  | On-Hold | Faster completion ETL jobs and and this is associated to the items in Row 60 and 61
NA | CMT | JJDCC | Process Improvement | BEST PRACTICE | BEST PRACTICES | 12 | Vinod/Raj | Re-organise the Cognos folder structure | Q4 | Anand/Charan | TBD | 0 | 0 | 0 | 0 |  | On-Hold | Reduction in manual activity and easy navigation to the report location
ASPAC | CMT | MIRA | Process Improvement | BEST PRACTICE | BEST PRACTICES | 59 | Vibhas/Raj | Adding DB, ETL and MSTR in Source safe in ASPAC | Q4 | shankar | [6 empty] | Planned
LSGPS | CMT | MIRA | Process Improvement | BEST PRACTICE | BEST PRACTICES | 60 | Vibhas/Raj | Adding DB, ETL and MSTR in Source safe in LSGPS | Q4 | shankar | [6 empty] | Planned
NA | CMT | MIRA | Process Improvement | BEST PRACTICE | BEST PRACTICES | 58 | Vibhas/Raj | Adding DB, ETL and MSTR in Source safe in NA | Q4 | shankar | [6 empty] | Planned
nA | CMT | MIRA | Automation | BEST PRACTICE | ASO |  | Vibhas/Raj | Automate to load the MIRA incident and SR into the database. | 2018 | shankar | [6 empty] | Planned
NA | CMT | MIRA | Process Improvement | BEST PRACTICE | BEST PRACTICES | 32 | Vibhas/Raj | Create logs for high CPU utilization : This script will logs the max CPU consuming process with process details on a hourly basis. It will help the team to analyze outages. It will help for proactive monitoring. | Q3 | Sourav | 10 | 0 | 0 |  |  | NA | Planned
NA | CMT | MIRA | Automation | BEST PRACTICE | BEST PRACTICES | 61 | Vibhas/Raj | Creation of a tool/script to send outage emails with the required format of the mail | Q4 | Rishiraj | [6 empty] | Planned
ASPAC | CMT | MIRA | Automation | BEST PRACTICE | BEST PRACTICES | 62 | Vibhas/Raj | Creation of a tool/script to send outage emails with the required format of the mail | Q4 | Rishiraj | [6 empty] | Planned
LSGPS | CMT | MIRA | Automation | BEST PRACTICE | BEST PRACTICES | 63 | Vibhas/Raj | Creation of a tool/script to send outage emails with the required format of the mail | Q4 | Rishiraj | [6 empty] | Planned
NA | CMT | MIRA | Process Improvement | BEST PRACTICE | BEST PRACTICES | 39 | Vibhas/Raj | Reschedule Call job in NA PROD | Q3 | Muthu |  | 0 |  |  |  | NA | Planned
NA | CMT | MIRA | Process Improvement | BEST PRACTICE | BEST PRACTICES | 36 | Vibhas/Raj | Reschedule Customer in NA PROD | Q3 | Muthu |  | 0 |  |  |  | NA | Planned
NA | CMT | MIRA | Process Improvement | BEST PRACTICE | BEST PRACTICES | 37 | Vibhas/Raj | Reschedule Mbox delivery in NA PROD | Q3 | Muthu |  | 0 |  |  |  | NA | Planned |  | 100%
NA | CMT | MIRA | Process Improvement | BEST PRACTICE | BEST PRACTICES | 35 | Vibhas/Raj | Reschedule RFP in NA PROD | Q3 | Muthu |  | 0 |  |  |  | NA | Planned
NA | CMT | MIRA | Process Improvement | BEST PRACTICE | BEST PRACTICES | 38 | Vibhas/Raj | Reschedule Sales job in NA PROD | Q3 | Muthu |  | 0 |  |  |  | NA | Planned |  | 20%
NA | CMT | JJDCC | Process Improvement | PERF.TUNING | ASO | 9 | Vinod/Raj | Middle east processing | Q4 | Kishore/Nageswar | TBD | TBD |  |  |  |  | On-Hold | 14 service requests. 25-30 manual hours/month reduction
NA | CMT | JJDCC | Process Improvement | PERF.TUNING | ASO | 7 | Vinod/Raj | Analyze LEO long running jobs and identify possible improvements | Q3 | Naresh/Biswa | 50 | [5 empty] | On-Hold | 4 Incidents. Faster completion ETL jobs and timely availability of data to user
NA | CMT | JJDCC | Performance tuning | PERF.TUNING | ASO | 20 | Vinod/Raj | EMEA SSIS jobs improvement | Q4 | Anand/Charan | TBD | 60 | 60 |  |  |  | Planned | 1 Incident. Avoid job failure and On time completion of jobs
NA | CMT | MIRA | Performance tuning | PERF.TUNING | ASO | 34 | Vibhas/Raj | Optimize sales job to execute for better performance | Q3 | Raj |  | 189 |  |  |  | NA | Planned
ASPAC | CMT | myAcuvue | Technical Debt Reduction | PERF.TUNING | BEST PRACTICES | 2 | Shivakumar | The DIM tables loading pattern will be re-designed by changing the ETL jobs sequence to ensure that the Redshift Database resources are efficiently used. | Q3 | Roy | 40 | 0 |  |  |  | NA | Planned
NA | PHARMA | JSC EDW | Performance tuning | PERF.TUNING | ASO |  | Vibhas/Hamza | Query Optimization to PDP | October | JSCEDW Team | 14 | 0 | 0 | 0 | 0 | NA | Work in Progress
EMEA | MD | Beacon | Automation | Automation-Others | ASO |  | Vinod/Guru | Beacon Access Automation(Normal form) | Q3/Q4 | Karthik | 345 | 960 | 960 | 0 |  | 200 | Work in Progress | Automation of the Access request process. Completely elimantes the support effort
NA | CMT | MIRA | Automation | Automation-Others | ASO | 42 | Vibhas/Raj | Trigger call job once files are delivered from SFDC Team | Q3 | Shankar | 16 | 189 | 252 |  |  | NA | Planned
NA | CMT | MIRA | Automation | Automation-Others | ASO | 43 | Vibhas/Raj | Trigger Customer job once files are delivered from SAP BW Team | Q3 | Shankar | 16 | 63 | 63 |  |  | NA | Planned
NA | CMT | MIRA | Automation | Automation-Others | ASO | 29 | Vibhas/Raj | Trigger file to identify data load in MyACUVUE before cube refresh | Q3 | Sourav | 20 | 30 | 30 |  |  | NA | Planned |  | 0%
NA | CMT | MIRA | Automation | Automation-Others | ASO | 24 | Vibhas/Raj | Trigger jobs only when files are available (NA) | Q3 | Shankar | 16 | 63 | 63 |  |  | NA | Planned |  |  | 0
NA | CMT | JJDCC | Automation | Automation-Others | ASO | 2 | Vinod/Raj | TSA Automation | Q3 | Nageswara Rao | 50 | 84 | 100 |  |  |  | Work in progress | 06/22/2017- 06/19/2017-Working on alternative plan. 06/15/2017-Tim is excepting cost for SFTP service 06/12/2017-Today Nageshwar will be check with source team 4 service requests per month. Reduction of around 6-8 hours of manal effort 05/11/2017--Unable to access IMS portal,that's the reason reach out to Network and windows teams, now i got the acees but iam unable to login, so i need to engage with appropriate team to resolve the same | 30%
ASPAC | CMT | MIRA | Automation | Automation-Others | ASO | 17 | Vibhas/Raj | Trigger jobs only when files are available (ASPAC) | August | Kavya | 60 | 720 | 720 |  |  | NA | Work in Progress | each region requires 1hr/day to monitor
NA | PHARMA | JSC EDW | Automation | Automation-Others | ASO | 8 | Vibhas/Hamza | Health Check automation: Planned for automation manual work takes around two hour of time everyday | 2017-06-01 | Shruti Hegde | 40 | 520 | 520 |  |  | NA | Work in Progress
NA | CMT | MIRA | Automation | Automation-Others | ASO | 13 | Vibhas/Raj | ETL package to add multiple users NA | August | Kavya | 16 | 96 | 120 |  |  | NA | Work in Progress | Savings: 1 hr/request; approx 8 tickets per month | 50%
NA | CMT | MIRA | Automation | Automation-Others | ASO | 57 | Vibhas/Raj | Automate clearing of MSTR dump files I-server NA | Q4 | Rishiraj | 10 | 26 | 52 |  |  | NA | Planned
NA | CMT | MIRA | Shift-Left/Self Help | SHIFT LEFT | BEST PRACTICES | 55 | Vibhas/Raj | Dcoumentation of steps for resolution of incident | Q4 | Team | TBD | 0 | 0 | 0 | 0 | NA | Planned | This falls under process improvement.
NA | CMT | JJDCC | Process Improvement | SHIFT LEFT | BEST PRACTICES | 18 | Vinod/Raj | Mapping sheet for all source,ETL , Target table and Cognos reports | Q2/Q3 | Biswaranjan | 60 | 0 | 0 | 0 | 0 |  | Work in Progress | 05/11/2017-- one catalog done. Good Knowledge base
NA | CMT | JJDCC | Process Improvement | SHIFT LEFT | BEST PRACTICES | 19 | Vinod/Raj | SOP for frequent service requests | Q3 | Anand | 50 | 0 | 0 | 0 | 0 |  | Work in Progress | 5 Service Requests. Reduction in Service Requests
NA | CMT | JJDCC, Vision Care | Process Improvement | SHIFT LEFT | BEST PRACTICES | 23 | Vinod/Raj | Knowledge Documents (Ongoing) | Q2/Q3/Q4 | Team | 50 | 0 | 0 | 0 | 0 |  | Work in progress | Knowledge Base
NA | PHARMA | IQLIK | Automation | SMART ANALYTICS-Manual | ASO |  | Vibhas/Hamza | Automation of Manual process in QLIKSENSE QVD refresh | Nov 10th | IQLIK Team | To be estimated | [5 empty] | In Progress
NA | CMT | JJDCC | Automation | SMART ANALYTICS-Manual | ASO | 3 | Vinod/Raj | Sales and Marketing Automation | Q4 | Nageswara Rao/Naresh | TBD | 24 | 30 |  |  |  | On-Hold | 1 service request per month. Reduction of around 4-6 hours of manal effort
NA | CMT | Vision Care | Automation | SMART ANALYTICS-Manual | ASO | 22 | Vinod/Raj | Scheduling Vision care ASPAC jobs on Tidal | August | Lokesh | 20 | 50 | 50 |  |  | NA | On-Hold | Pending for Approval to deploy in Prod
NA | PHARMA | GBI | Automation | SMART ANALYTICS-Manual | ASO | 51 | Prashanth M/ Hamza | Spec Sheet automation for removing manual intervention | Q2 | Team | 40 | 120 | 0 | 0 | 0 | NA | Planned | This is planned to remove manual intervention
NA | PHARMA | GBI | Automation | SMART ANALYTICS-Manual | ASO | 2 | Prashanth M/Hamza | EDW ETA estimation | Q3 | Sathish/Nilanjan/Pandarinath | 80 | 104 | 104 |  |  | NA | Planned | Possibility of automation in calculation of ETA
NA | CMT | MIRA | Automation | SMART ANALYTICS-Manual | ASO | 19 | Vibhas/Raj | Automate daily reconciliation of NA Vistakon Sales data | August | Shankar | 60 | 384 | 384 |  |  | 24 | Planned | Reduction in data mismatch incidents; approx 2 per month; savings: 16 hrs per incident
NA | CMT | MIRA | Automation | SMART ANALYTICS-Manual | ASO | 53 | Vibhas/Raj | Automate data load for Quota and compensation for NA | Q4 | Shankar | 24 | 20 | 20 |  |  | NA | Planned | Savings:5 hrs/Per Quarter. This activity has to be done every Quarter
NA | CMT | MIRA | Automation | SMART ANALYTICS-Manual | ASO | 47 | Vibhas/Raj | Automate the campaign file | Q4 | Shekar | 16 | 48 | 48 |  |  | NA | Planned | We will get a request to refresh campaign file so we are doing manually as of now so we need to do automation
NA | CMT | MIRA | Automation | SMART ANALYTICS-Manual | ASO | 46 | Vibhas/Raj | Automate the daily job monitory activity (dashboard to view all jobs) - This needs to be have feasibility study as well..so Q4 | Q4 | Shankar | 200 | 396 | 528 |  |  | NA | Planned | Savings: 15 mins per server; 6 servers; 5 days per week | 0%
ASPAC | CMT | MIRA | Automation | SMART ANALYTICS-Manual | ASO | 30 | Vibhas/Raj | Automate the Japan KPI Metrics from Enterprise Manager | Q3 | Anil | 60 | 192 | 192 |  |  | NA | Planned | Savings:16hrs/month. This activity has to be done every month
NA | CMT | MIRA | Automation | SMART ANALYTICS-Manual | ASO | 45 | Vibhas/Raj | Automating the migration tasks (DB) | Q4 | Shekar | 16 | 18 | 72 |  |  | NA | Planned | Savings: 25 mins per deployment; Assumption: 2 deployments per month (QA/PROD); 3 regions
NA | PHARMA | GBI | Automation | SMART ANALYTICS-Manual | ASO | 1 | Prashanth M/Hamza | EDW Dashboard E-Mail Automation : EDW Dashboard needs to be manually prepared collecting data for each job separately through the Tidal Console. This is consuming significant time and effort on a daily basis. | 2017-05-01 | Sathish/Nilanjan/Pandarinath | 80 | 365 | 426 |  |  | NA | Work in Progress
NA | PHARMA | GBI | Automation | SMART ANALYTICS-Manual | ASO | 4 | Prashanth M/Hamza | Manual activities related to cognos Weekly immunology activity. --> Executing the cubes IBM Cognos Transformer cubes from tidal. --> Moving of the mdc files into corresponding folders. --> Implementation of automation scripts for Backup process . | 2017-05-01 | Hemasundar/Pandarinath | 40 | 208 | 208 |  |  | NA | Work in Progress
NA | PHARMA | JSC EDW | Automation | SMART ANALYTICS-REC INC | ASO |  | Vibhas/Hamza | Project team identified that INSP_LOT & DOC TABLE are loading parallelly but INSP_LOT TABLE is using the data from DOC table.Ideally, there should have been a dependency of DOC table on INSP_LOT.We are working on fixing the dependencies, | August | Ramakrishna | 10 | [5 empty] | On-Hold | Analysis is in progress
NA | PHARMA | JSC EDW | Automation | SMART ANALYTICS-REC INC | ASO |  | Vibhas/Hamza | We have faced failures due to MASTER data & CROSS REF files having leading spaces for the sitenames & other description columns.Ø PARTY table failed due to unique key constraint , and when we analyzed found that the master data was updated with spaces | August | Krishna B | 60 | [5 empty] | On-Hold | Analysis is in progress
NA | CMT | MIRA | Process Improvement | SMART ANALYTICS-REC INC | ASO | 33 | Vibhas/Raj | Implement delete and archive for NA ETL instead of copy and paste | Q3 | Shekar | 50 | 40 | 40 |  |  | 1 | Planned | recieved one incident because of which data was duplicated. implement better etl solutions like archiving files and deleting the files. Assuming will receive 1 incident pere quarter | 0%
NA | CMT | MIRA | Process Improvement | SMART ANALYTICS-REC INC | ASO | 54 | Vibhas/Raj | Option to delete user specific cache on Ipad | Q4 | Anil | 40 | 12 | 12 |  |  | 4 | Planned | 4 tickets per month. 1 ticket takes 15mins | 90%
ASPAC | CMT | MIRA | Process Improvement | SMART ANALYTICS-REC INC | ASO | 40 | Vibhas/Raj | We need to access ASAPC QA and PROD FROM DEV server in different region | Q3 | Sourav | 30 | 288 | 1152 |  |  | NA | Planned | Now we are unable to access the ASPAC QA or PROD server from the DEV. Currently taking 8 hours by this will reduce to 4 we need some AWS configurations changes to do this . | 100%
NA | CMT | MIRA | Process Improvement | SMART ANALYTICS-REC INC | ASO | 14 | Vibhas/Raj | MBOX configuration for NA Call Files | August | Shekar | 18 | 104 | 104 |  |  | 8 | Work in Progress | Savings: 2hrs per week; 2 tickets per week (one for QA and another for PROD) | 70%
ASPAC | CMT | MIRA | Automation | SMART ANALYTICS-SR | ASO | 51 | Vibhas/Raj | Environment Sync -> creation of ETL to load data from PROD to QA -- ASPAC | August | Shekar | 16 | 36 | 36 |  |  | 12 | Planned | Savings: 3 hr for each sync; approx 1 env sync requests per month due to data mismatch between prod & qa
LSGPS | CMT | MIRA | Automation | SMART ANALYTICS-SR | ASO | 52 | Vibhas/Raj | Environment Sync -> creation of ETL to load data from PROD to QA -- LSGPS | August | Shankar | 16 | 36 | 36 |  |  | 12 | Planned | Savings: 3 hr for each sync; approx 1 env sync requests per month due to data mismatch between prod & qa | 20%
NA | CMT | MIRA | Automation | SMART ANALYTICS-SR | ASO | 31 | Vibhas/Raj | Syncronization of Dev , Qa and Prod environments on MSTR | August | Rishiraj | 45 | 144 | 144 |  |  | 12 | Planned | Data Validation in progress | 85%
245
220
40
505
| 5.05 |  |  |  | 429
|  | 189 | 150
|  | 185 | 180
|  | 245 | 220
|  |  | 220 |  |  |  | 1914
245
|  | 81.6667 | 40
|  | 105.6 | 505
|  | 1.2931 | 6.3125
429
|  | 6.1869 |  | 5.3625
5700
|  | 132 |  | 95
44
139
0.86875

## Notes from Roji
APMON for application performance monitoring
IKON for Knowledge management/KEDB
what tools currently in use in JNJ
Can we introduce new tools..
Chatbots..request for information from user..using slack for L1.5..Monitroing tool feeds data into chat window..
self-healing-remediation
Rule based bots
SAP : SOLMON (are they using this tool and using it to full extent)
how to escalate to next level : Auto escalation
assign ticket to right support team..data analysis to create a rule..
Business BOTs
what we have done in 2017
what we are planning in 2018
what is the roadmap for future next 2 yrs
Slack : like sype with multiple Channels
search automation of knowledge base(sinequa)
Chatbot(How do I, service request, monitoring status, background check)
virtual assistant COE (Tools used, accelerators
APM COE (More on the monitoring)